{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Data","Temp","Daily","Color"],"not_rendered":{"charts":1,"images":0,"macros":1,"external_links":0,"defined_names":6,"comments":1,"pivot_tables":3},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Data","index":0,"n_rows":54,"n_cols":24,"rows_kept":54,"cut":false,"hidden":false,"merged":[]}
[]
[null,null,"PivotTable2",null,"Table2",null,null,"PivotTable1"]
[null,null,"Count of Value",null,"House","Count",null,"Sum of DDate","Seq"]
[null,null,75,null,1,{"$f":"2*COUNTIFS(Table1[House],Table2[[#This Row],[House]])","v":16},null,"House",1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16]
[null,null,null,null,2,{"$f":"2*COUNTIFS(Table1[House],Table2[[#This Row],[House]])","v":16},null,1,null,"2012-01-04",0,5,2,7,3,6,6,3,2,5,5,2,8,5]
[null,null,null,null,3,{"$f":"2*COUNTIFS(Table1[House],Table2[[#This Row],[House]])","v":16},null,2,null,"2012-01-04",2,5,4,7,3,6,6,3,2,5,5,4,8,5]
[null,null,null,null,4,{"$f":"2*COUNTIFS(Table1[House],Table2[[#This Row],[House]])","v":16},null,3,null,"2012-01-04",4,5,6,7,3,6,3,3,4,7,5,2,8,7]
[null,null,null,null,5,{"$f":"2*COUNTIFS(Table1[House],Table2[[#This Row],[House]])","v":16},null,4,null,"2012-01-04",6,5,6,7,5,6,3,3,2,6,5,2,8,5]
[null,null,null,null,null,null,null,5,null,"2012-01-04",8,5,8,7,5,6,6,3,2,5,5,2,8,5]
[]
[]
[]
[null,null,"Table1",null,null,null,null,"PivotChart"]
[null,null,"House","Activity","Start","Stop"]
[null,null,1,null,null,{"$f":"INT(MIN(Table1[Start]))","v":"2012-01-04"}]
[null,null,1,"Slab","2012-01-04",{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-01-09"}]
[null,null,1,"Wall",{"$f":"F16+2","v":"2012-01-11"},{"$f":"Table1[[#This Row],[Start]]+7","v":"2012-01-18"}]
[null,null,1,"Roof",{"$f":"E17+10","v":"2012-01-21"},{"$f":"Table1[[#This Row],[Start]]+6","v":"2012-01-27"}]
[null,null,1,"Gas",{"$f":"E18+12","v":"2012-02-02"},{"$f":"Table1[[#This Row],[Start]]+3","v":"2012-02-05"}]
[null,null,1,"Elect",{"$f":"E19+5","v":"2012-02-07"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-02-12"}]
[null,null,1,"Plumb",{"$f":"E20+10","v":"2012-02-17"},{"$f":"Table1[[#This Row],[Start]]+2","v":"2012-02-19"}]
[null,null,1,"Finishes",{"$f":"E21+10","v":"2012-02-27"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-03-03"}]
[null,null,2,null,null,{"$f":"INT(MIN(Table1[Start]))","v":"2012-01-04"}]
[null,null,2,"Slab",{"$f":"E16+2","v":"2012-01-06"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-01-11"}]
[null,null,2,"Wall",{"$f":"E17+4","v":"2012-01-15"},{"$f":"Table1[[#This Row],[Start]]+7","v":"2012-01-22"}]
[null,null,2,"Roof",{"$f":"E18+4","v":"2012-01-25"},{"$f":"Table1[[#This Row],[Start]]+6","v":"2012-01-31"}]
[null,null,2,"Gas",{"$f":"F26+6","v":"2012-02-06"},{"$f":"Table1[[#This Row],[Start]]+3","v":"2012-02-09"}]
[null,null,2,"Elect",{"$f":"F27+2","v":"2012-02-11"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-02-16"}]
[null,null,2,"Plumb",{"$f":"F28+5","v":"2012-02-21"},{"$f":"Table1[[#This Row],[Start]]+4","v":"2012-02-25"}]
[null,null,2,"Finishes",{"$f":"F29+8","v":"2012-03-04"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-03-09"}]
[null,null,3,null,null,{"$f":"INT(MIN(Table1[Start]))","v":"2012-01-04"}]
[null,null,3,"Slab",{"$f":"E24+2","v":"2012-01-08"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-01-13"}]
[null,null,3,"Wall",{"$f":"E25+4","v":"2012-01-19"},{"$f":"Table1[[#This Row],[Start]]+7","v":"2012-01-26"}]
[null,null,3,"Roof",{"$f":"E26+4","v":"2012-01-29"},{"$f":"Table1[[#This Row],[Start]]+6","v":"2012-02-04"}]
[null,null,3,"Gas",{"$f":"F34+3","v":"2012-02-07"},{"$f":"Table1[[#This Row],[Start]]+3","v":"2012-02-10"}]
[null,null,3,"Elect",{"$f":"F35+4","v":"2012-02-14"},{"$f":"Table1[[#This Row],[Start]]+7","v":"2012-02-21"}]
[null,null,3,"Plumb",{"$f":"F36+5","v":"2012-02-26"},{"$f":"Table1[[#This Row],[Start]]+2","v":"2012-02-28"}]
[null,null,3,"Finishes",{"$f":"F37+8","v":"2012-03-07"},{"$f":"Table1[[#This Row],[Start]]+7","v":"2012-03-14"}]
[null,null,4,null,null,{"$f":"INT(MIN(Table1[Start]))","v":"2012-01-04"}]
[null,null,4,"Slab",{"$f":"E32+2","v":"2012-01-10"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-01-15"}]
[null,null,4,"Wall",{"$f":"E33+2","v":"2012-01-21"},{"$f":"Table1[[#This Row],[Start]]+7","v":"2012-01-28"}]
[null,null,4,"Roof",{"$f":"E34+4","v":"2012-02-02"},{"$f":"Table1[[#This Row],[Start]]+6","v":"2012-02-08"}]
[null,null,4,"Gas",{"$f":"F42+3","v":"2012-02-11"},{"$f":"Table1[[#This Row],[Start]]+3","v":"2012-02-14"}]
[null,null,4,"Elect",{"$f":"F43+2","v":"2012-02-16"},{"$f":"Table1[[#This Row],[Start]]+6","v":"2012-02-22"}]
[null,null,4,"Plumb",{"$f":"F44+5","v":"2012-02-27"},{"$f":"Table1[[#This Row],[Start]]+2","v":"2012-02-29"},null,"For a macro-free PowerPivot version see:"]
[null,null,4,"Finishes",{"$f":"F45+8","v":"2012-03-08"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-03-13"},null,"http://www.mediafire.com/view/umvqagmx94lebns/11_16_12.xlsx"]
[null,null,5,null,null,{"$f":"INT(MIN(Table1[Start]))","v":"2012-01-04"}]
[null,null,5,"Slab",{"$f":"E40+2","v":"2012-01-12"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-01-17"}]
[null,null,5,"Wall",{"$f":"E41+4","v":"2012-01-25"},{"$f":"Table1[[#This Row],[Start]]+7","v":"2012-02-01"}]
[null,null,5,"Roof",{"$f":"E42+4","v":"2012-02-06"},{"$f":"Table1[[#This Row],[Start]]+6","v":"2012-02-12"}]
[null,null,5,"Gas",{"$f":"F50+6","v":"2012-02-18"},{"$f":"Table1[[#This Row],[Start]]+3","v":"2012-02-21"}]
[null,null,5,"Elect",{"$f":"F51+2","v":"2012-02-23"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-02-28"}]
[null,null,5,"Plumb",{"$f":"F52+5","v":"2012-03-04"},{"$f":"Table1[[#This Row],[Start]]+2","v":"2012-03-06"}]
[null,null,5,"Finishes",{"$f":"F53+8","v":"2012-03-14"},{"$f":"Table1[[#This Row],[Start]]+5","v":"2012-03-19"}]

{"sheet":"Temp","index":1,"n_rows":81,"n_cols":4,"rows_kept":81,"cut":false,"hidden":false,"merged":[]}
["House","Activity","Seq","DDate"]
[1,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":1}]
[1,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":2},"2012-01-04"]
[1,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":3},"2012-01-04"]
[1,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":4},"2012-01-09"]
[1,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":5},"2012-01-11"]
[1,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":6},"2012-01-18"]
[1,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":7},"2012-01-21"]
[1,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":8},"2012-01-27"]
[1,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":9},"2012-02-02"]
[1,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":10},"2012-02-05"]
[1,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":11},"2012-02-07"]
[1,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":12},"2012-02-12"]
[1,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":13},"2012-02-17"]
[1,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":14},"2012-02-19"]
[1,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":15},"2012-02-27"]
[1,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":16},"2012-03-03"]
[2,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":1}]
[2,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":2},"2012-01-04"]
[2,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":3},"2012-01-06"]
[2,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":4},"2012-01-11"]
[2,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":5},"2012-01-15"]
[2,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":6},"2012-01-22"]
[2,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":7},"2012-01-25"]
[2,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":8},"2012-01-31"]
[2,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":9},"2012-02-06"]
[2,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":10},"2012-02-09"]
[2,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":11},"2012-02-11"]
[2,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":12},"2012-02-16"]
[2,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":13},"2012-02-21"]
[2,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":14},"2012-02-25"]
[2,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":15},"2012-03-04"]
[2,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":16},"2012-03-09"]
[3,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":1}]
[3,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":2},"2012-01-04"]
[3,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":3},"2012-01-08"]
[3,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":4},"2012-01-13"]
[3,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":5},"2012-01-19"]
[3,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":6},"2012-01-26"]
[3,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":7},"2012-01-29"]
[3,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":8},"2012-02-04"]
[3,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":9},"2012-02-07"]
[3,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":10},"2012-02-10"]
[3,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":11},"2012-02-14"]
[3,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":12},"2012-02-21"]
[3,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":13},"2012-02-26"]
[3,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":14},"2012-02-28"]
[3,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":15},"2012-03-07"]
[3,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":16},"2012-03-14"]
[4,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":1}]
[4,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":2},"2012-01-04"]
[4,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":3},"2012-01-10"]
[4,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":4},"2012-01-15"]
[4,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":5},"2012-01-21"]
[4,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":6},"2012-01-28"]
[4,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":7},"2012-02-02"]
[4,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":8},"2012-02-08"]
[4,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":9},"2012-02-11"]
[4,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":10},"2012-02-14"]
[4,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":11},"2012-02-16"]
[4,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":12},"2012-02-22"]
[4,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":13},"2012-02-27"]
[4,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":14},"2012-02-29"]
[4,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":15},"2012-03-08"]
[4,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":16},"2012-03-13"]
[5,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":1}]
[5,null,{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":2},"2012-01-04"]
[5,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":3},"2012-01-12"]
[5,"Slab",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":4},"2012-01-17"]
[5,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":5},"2012-01-25"]
[5,"Wall",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":6},"2012-02-01"]
[5,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":7},"2012-02-06"]
[5,"Roof",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":8},"2012-02-12"]
[5,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":9},"2012-02-18"]
[5,"Gas",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":10},"2012-02-21"]
[5,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":11},"2012-02-23"]
[5,"Elect",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":12},"2012-02-28"]
[5,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":13},"2012-03-04"]
[5,"Plumb",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":14},"2012-03-06"]
[5,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":15},"2012-03-14"]
[5,"Finishes",{"$f":"COUNTIF(INDEX(Table3[House],1):Table3[[#This Row],[House]],Table3[[#This Row],[House]])","v":16},"2012-03-19"]

{"sheet":"Daily","index":2,"n_rows":211,"n_cols":11,"rows_kept":211,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"Table4",null,null,null,null,null,null,"PivotTable"]
[null,"House","Activity","Start","Stop","DDays",null,null,"Activity","House","Sum of DDays"]
[null,1,"Slab","2012-01-04","2012-01-05",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,"Elect",null,28]
[null,1,"Slab","2012-01-05","2012-01-06",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,1,5]
[null,1,"Slab","2012-01-06","2012-01-07",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,2,5]
[null,1,"Slab","2012-01-07","2012-01-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,3,7]
[null,1,"Slab","2012-01-08","2012-01-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,4,6]
[null,1,"Slab","2012-01-09","2012-01-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0},null,null,null,5,5]
[null,1,"Wall","2012-01-11","2012-01-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,"Finishes",null,27]
[null,1,"Wall","2012-01-12","2012-01-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,1,5]
[null,1,"Wall","2012-01-13","2012-01-14",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,2,5]
[null,1,"Wall","2012-01-14","2012-01-15",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,3,7]
[null,1,"Wall","2012-01-15","2012-01-16",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,4,5]
[null,1,"Wall","2012-01-16","2012-01-17",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,5,5]
[null,1,"Wall","2012-01-17","2012-01-18",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,"Gas",null,15]
[null,1,"Wall","2012-01-18","2012-01-18",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0},null,null,null,1,3]
[null,1,"Roof","2012-01-21","2012-01-22",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,2,3]
[null,1,"Roof","2012-01-22","2012-01-23",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,3,3]
[null,1,"Roof","2012-01-23","2012-01-24",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,4,3]
[null,1,"Roof","2012-01-24","2012-01-25",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,5,3]
[null,1,"Roof","2012-01-25","2012-01-26",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,"Plumb",null,12]
[null,1,"Roof","2012-01-26","2012-01-27",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,1,2]
[null,1,"Roof","2012-01-27","2012-01-27",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0},null,null,null,2,4]
[null,1,"Gas","2012-02-02","2012-02-03",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,3,2]
[null,1,"Gas","2012-02-03","2012-02-04",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,4,2]
[null,1,"Gas","2012-02-04","2012-02-05",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,5,2]
[null,1,"Gas","2012-02-05","2012-02-05",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0},null,null,"Roof",null,30]
[null,1,"Elect","2012-02-07","2012-02-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,1,6]
[null,1,"Elect","2012-02-08","2012-02-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,2,6]
[null,1,"Elect","2012-02-09","2012-02-10",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,3,6]
[null,1,"Elect","2012-02-10","2012-02-11",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,4,6]
[null,1,"Elect","2012-02-11","2012-02-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,5,6]
[null,1,"Elect","2012-02-12","2012-02-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0},null,null,"Slab",null,25]
[null,1,"Plumb","2012-02-17","2012-02-18",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,1,5]
[null,1,"Plumb","2012-02-18","2012-02-19",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,2,5]
[null,1,"Plumb","2012-02-19","2012-02-19",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0},null,null,null,3,5]
[null,1,"Finishes","2012-02-27","2012-02-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,4,5]
[null,1,"Finishes","2012-02-28","2012-02-29",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,5,5]
[null,1,"Finishes","2012-02-29","2012-03-01",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,"Wall",null,35]
[null,1,"Finishes","2012-03-01","2012-03-02",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,1,7]
[null,1,"Finishes","2012-03-02","2012-03-03",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,2,7]
[null,1,"Finishes","2012-03-03","2012-03-03",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0},null,null,null,3,7]
[null,2,"Slab","2012-01-06","2012-01-07",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,4,7]
[null,2,"Slab","2012-01-07","2012-01-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,null,5,7]
[null,2,"Slab","2012-01-08","2012-01-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1},null,null,"Grand Total",null,172]
[null,2,"Slab","2012-01-09","2012-01-10",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Slab","2012-01-10","2012-01-11",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Slab","2012-01-11","2012-01-11",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,2,"Wall","2012-01-15","2012-01-16",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Wall","2012-01-16","2012-01-17",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Wall","2012-01-17","2012-01-18",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Wall","2012-01-18","2012-01-19",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Wall","2012-01-19","2012-01-20",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Wall","2012-01-20","2012-01-21",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Wall","2012-01-21","2012-01-22",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Wall","2012-01-22","2012-01-22",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,2,"Roof","2012-01-25","2012-01-26",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Roof","2012-01-26","2012-01-27",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Roof","2012-01-27","2012-01-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Roof","2012-01-28","2012-01-29",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Roof","2012-01-29","2012-01-30",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Roof","2012-01-30","2012-01-31",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Roof","2012-01-31","2012-01-31",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,2,"Gas","2012-02-06","2012-02-07",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Gas","2012-02-07","2012-02-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Gas","2012-02-08","2012-02-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Gas","2012-02-09","2012-02-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,2,"Elect","2012-02-11","2012-02-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Elect","2012-02-12","2012-02-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Elect","2012-02-13","2012-02-14",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Elect","2012-02-14","2012-02-15",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Elect","2012-02-15","2012-02-16",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Elect","2012-02-16","2012-02-16",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,2,"Plumb","2012-02-21","2012-02-22",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Plumb","2012-02-22","2012-02-23",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Plumb","2012-02-23","2012-02-24",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Plumb","2012-02-24","2012-02-25",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Plumb","2012-02-25","2012-02-25",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,2,"Finishes","2012-03-04","2012-03-05",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Finishes","2012-03-05","2012-03-06",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Finishes","2012-03-06","2012-03-07",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Finishes","2012-03-07","2012-03-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Finishes","2012-03-08","2012-03-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,2,"Finishes","2012-03-09","2012-03-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,3,"Slab","2012-01-08","2012-01-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Slab","2012-01-09","2012-01-10",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Slab","2012-01-10","2012-01-11",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Slab","2012-01-11","2012-01-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Slab","2012-01-12","2012-01-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Slab","2012-01-13","2012-01-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,3,"Wall","2012-01-19","2012-01-20",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Wall","2012-01-20","2012-01-21",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Wall","2012-01-21","2012-01-22",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Wall","2012-01-22","2012-01-23",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Wall","2012-01-23","2012-01-24",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Wall","2012-01-24","2012-01-25",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Wall","2012-01-25","2012-01-26",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Wall","2012-01-26","2012-01-26",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,3,"Roof","2012-01-29","2012-01-30",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Roof","2012-01-30","2012-01-31",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Roof","2012-01-31","2012-02-01",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Roof","2012-02-01","2012-02-02",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Roof","2012-02-02","2012-02-03",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Roof","2012-02-03","2012-02-04",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Roof","2012-02-04","2012-02-04",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,3,"Gas","2012-02-07","2012-02-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Gas","2012-02-08","2012-02-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Gas","2012-02-09","2012-02-10",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Gas","2012-02-10","2012-02-10",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,3,"Elect","2012-02-14","2012-02-15",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Elect","2012-02-15","2012-02-16",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Elect","2012-02-16","2012-02-17",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Elect","2012-02-17","2012-02-18",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Elect","2012-02-18","2012-02-19",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Elect","2012-02-19","2012-02-20",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Elect","2012-02-20","2012-02-21",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Elect","2012-02-21","2012-02-21",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,3,"Plumb","2012-02-26","2012-02-27",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Plumb","2012-02-27","2012-02-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Plumb","2012-02-28","2012-02-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,3,"Finishes","2012-03-07","2012-03-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Finishes","2012-03-08","2012-03-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Finishes","2012-03-09","2012-03-10",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Finishes","2012-03-10","2012-03-11",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Finishes","2012-03-11","2012-03-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Finishes","2012-03-12","2012-03-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Finishes","2012-03-13","2012-03-14",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,3,"Finishes","2012-03-14","2012-03-14",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,4,"Slab","2012-01-10","2012-01-11",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Slab","2012-01-11","2012-01-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Slab","2012-01-12","2012-01-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Slab","2012-01-13","2012-01-14",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Slab","2012-01-14","2012-01-15",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Slab","2012-01-15","2012-01-15",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,4,"Wall","2012-01-21","2012-01-22",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Wall","2012-01-22","2012-01-23",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Wall","2012-01-23","2012-01-24",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Wall","2012-01-24","2012-01-25",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Wall","2012-01-25","2012-01-26",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Wall","2012-01-26","2012-01-27",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Wall","2012-01-27","2012-01-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Wall","2012-01-28","2012-01-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,4,"Roof","2012-02-02","2012-02-03",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Roof","2012-02-03","2012-02-04",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Roof","2012-02-04","2012-02-05",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Roof","2012-02-05","2012-02-06",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Roof","2012-02-06","2012-02-07",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Roof","2012-02-07","2012-02-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Roof","2012-02-08","2012-02-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,4,"Gas","2012-02-11","2012-02-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Gas","2012-02-12","2012-02-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Gas","2012-02-13","2012-02-14",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Gas","2012-02-14","2012-02-14",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,4,"Elect","2012-02-16","2012-02-17",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Elect","2012-02-17","2012-02-18",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Elect","2012-02-18","2012-02-19",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Elect","2012-02-19","2012-02-20",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Elect","2012-02-20","2012-02-21",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Elect","2012-02-21","2012-02-22",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Elect","2012-02-22","2012-02-22",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,4,"Plumb","2012-02-27","2012-02-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Plumb","2012-02-28","2012-02-29",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Plumb","2012-02-29","2012-02-29",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,4,"Finishes","2012-03-08","2012-03-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Finishes","2012-03-09","2012-03-10",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Finishes","2012-03-10","2012-03-11",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Finishes","2012-03-11","2012-03-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Finishes","2012-03-12","2012-03-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,4,"Finishes","2012-03-13","2012-03-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,5,"Slab","2012-01-12","2012-01-13",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Slab","2012-01-13","2012-01-14",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Slab","2012-01-14","2012-01-15",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Slab","2012-01-15","2012-01-16",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Slab","2012-01-16","2012-01-17",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Slab","2012-01-17","2012-01-17",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,5,"Wall","2012-01-25","2012-01-26",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Wall","2012-01-26","2012-01-27",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Wall","2012-01-27","2012-01-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Wall","2012-01-28","2012-01-29",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Wall","2012-01-29","2012-01-30",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Wall","2012-01-30","2012-01-31",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Wall","2012-01-31","2012-02-01",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Wall","2012-02-01","2012-02-01",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,5,"Roof","2012-02-06","2012-02-07",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Roof","2012-02-07","2012-02-08",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Roof","2012-02-08","2012-02-09",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Roof","2012-02-09","2012-02-10",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Roof","2012-02-10","2012-02-11",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Roof","2012-02-11","2012-02-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Roof","2012-02-12","2012-02-12",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,5,"Gas","2012-02-18","2012-02-19",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Gas","2012-02-19","2012-02-20",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Gas","2012-02-20","2012-02-21",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Gas","2012-02-21","2012-02-21",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,5,"Elect","2012-02-23","2012-02-24",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Elect","2012-02-24","2012-02-25",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Elect","2012-02-25","2012-02-26",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Elect","2012-02-26","2012-02-27",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Elect","2012-02-27","2012-02-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Elect","2012-02-28","2012-02-28",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,5,"Plumb","2012-03-04","2012-03-05",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Plumb","2012-03-05","2012-03-06",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Plumb","2012-03-06","2012-03-06",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]
[null,5,"Finishes","2012-03-14","2012-03-15",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Finishes","2012-03-15","2012-03-16",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Finishes","2012-03-16","2012-03-17",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Finishes","2012-03-17","2012-03-18",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Finishes","2012-03-18","2012-03-19",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":1}]
[null,5,"Finishes","2012-03-19","2012-03-19",{"$f":"Table4[[#This Row],[Stop]]-Table4[[#This Row],[Start]]","v":0}]

{"sheet":"Color","index":3,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
[null,"Table5"]
[null,"Color"]